## Test_Case
Centre Square Mall
VERSION NO: BROWSER:Chrome OS:Android |  |  |  | DATE:15/05/25
VERIFIED BY: |  |  |  | TESTED BY:Adarsh A S
Authentication
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
CSM_AU_001 | Register with Mobile number | Launch app → Register → Fill all valid fields → Submit | 9961690690 | Registration successful, OTP sent | Registration successful, OTP sent | Pass
CSM_AU_002 | Register with proper city | Launch app → Register → Fill all valid fields → Submit | Kollam | Registration successful, OTP sent | Registration successful, OTP sent | Pass
CSM_AU_003 | Register with improper city | Launch app → Register → Fill all valid fields → Submit | . | Error:invalid | Registration successful, OTP sent | Fail
CSM_AU_004 | Register with existing email | Use an already registered email | aadarsudarsanan123@gmail.com | Error: Email already registered | Registration successful, OTP sent | Fail
CSM_AU_005 | Register with invalid Email | Enter malformed email | usermail.com | Error: Invalid email format | Error: Invalid email format | Pass
CSM_AU_006 | Login with valid credentials | Enter correct Mobile number | 9961690690 | Login successful, redirected to dashboard | Login successful, redirected to dashboard | Pass
CSM_AU_007 | Session persists after restart | Login → Close and reopen app |  | Still logged in | Still logged in | Pass
CSM_AU_008 | Logout | Tap logout in profile |  | User redirected to login screen | User redirected to login screen | Pass
CSM_AU_009 | Re-register with deleted account number | Delete account → Try registering again | 9961690690 | Number accepted and new account created | Cannot login | Fail
MY Account
CSM_MA_010 | View profile info | Launch app → Profile → Profile |  | Profile details are displayed | Profile details are displayed | Pass
CSM_MA_011 | Edit name | Change fields and save | Hari | Details updated | Details updated | Pass
CSM_MA_012 | Update With invalid email | Change fields and save | .com | Error:Invalid name | Error:Invalid name | Pass
CSM_MA_013 | Update Without name | Change fields and save |  | Error:Invalid name | Error:Invalid name | Pass
CSM_MA_014 | Upload profile picture | Upload a valid image | JPEG/PNG image | Image uploaded | Image uploaded | Pass
CSM_MA_015 | Save profile with empty fields | Clear mandatory fields and save | Empty name/phone | Error: Required fields | Error: Required fields | Pass
CSM_MA_016 | update interests counts | Select 4 interets |  | profile Updated | update successful | Pass
CSM_MA_017 | update with improper city | Change Name field | . | Error:invalid city name | update successful | Fail
CSM_MA_018 | View parking QR | Launch app → Profile → Parking QR |  | Show parking QR | Show parking QR | Pass
CSM_MA_019 | View Notifications | Launch app → Profile → notifications |  | Show notifications | notifications dispalyed | Pass
CSM_MA_020 | View bills | Launch app → Profile → my Bills |  | Show claimed bills,under review bills and rejected bills | Show claimed bills,under review bills and rejected bills | Pass
CSM_MA_021 | View my referrels | Launch app → Profile → my referels |  | show referred peopls | Not showing refered people | Fail
CSM_MA_022 | View mall info | Launch app → Profile → Mall info |  | show mall info | show mall info | Pass
CSM_MA_023 | view interesed events and stores | Launch app → Profile → interested |  | view interesed events and stores | view interesed events and stores | Pass
CSM_MA_024 | view privacy policy | Launch app → Profile → privacy policy |  | view privacy policy | view privacy policy | Pass
CSM_MA_025 | view terms and conditions | Launch app → Profile → terms and conditions |  | view terms and conditions | view terms and conditions | Pass
CSM_MA_026 | share invite link | Launch app → Profile → invite |  | share invite link | share invite link | Pass
CSM_MA_027 | Help and support | Launch app → Profile → Help and Support |  | View help and Support | View help and Support | Pass
CSM_MA_028 | Tap on support contact number redirects to dialer | Launch app → Profile → Help and Support |  | Mobile dialer opens with number pre-filled | Dialer opens with correct number | Pass
CSM_MA_029 | Tap on email address opens default mail app | Launch app → Profile → Help and Support |  | Mail app opens with “To” field filled | Gmail app opens with email filled | Pass
CSM_MA_030 | Contact number is clickable | Launch app → Profile → Help and Support |  | Number is highlighted as a tappable link | Number is clickable and functional | Pass
CSM_MA_031 | Email address is clickable | Launch app → Profile → Help and Support |  | Email appears as clickable text | Email is clickable and works | Pass
CSM_MA_032 | Support email opens with subject prefilled | Launch app → Profile → Help and Support |  | Opens mail app with subject like “Support Query” | Subject is filled as expected | Pass
CSM_MA_033 | Call completes successfully to support number | Launch app → Profile → Help and Support |  | Call connects to support without issue | Call rings and connects | Pass
CSM_MA_034 | Submit feedback with valid input | Launch app → Profile → Feedback | "Good service, thank you!" | Feedback submitted successfully | Feedback saved and acknowledged | Pass
CSM_MA_035 | Submit feedback with no character limit validation | Launch app → Profile → Feedback | "A" | Error shown for too short input | Feedback submitted with no warning | Fail
CSM_MA_036 | Submit very long feedback with 1000+ characters | Launch app → Profile → Feedback | 50+ characters | Input should be limited or truncated | Feedback submitted without restriction | Fail
CSM_MA_037 | Submit blank feedback (only space characters) | Launch app → Profile → Feedback | " " | Show error: "Feedback cannot be empty" | Show error: "Feedback cannot be empty" | Pass
CSM_MA_038 | Logout | Launch app → Profile → Logout |  | User redirected to login screen | User redirected to login screen | Pass
CSM_MA_039 | Delete account | Launch app → Profile → Delete account |  | Delete account and User redirected to login screen | Delete account and User redirected to login screen | Pass
Home
CSM_HO_040 | Referral link is not working | Launch app → Home → refer now |  | Redirects to app and applies referral code | Redirects to app store but no referral applied | Fail
CSM_HO_041 | No field to enter referral code during signup | Sign up with a fresh number |  | "Referral code" field visible and functional during registration | No referral code field shown | Fail
CSM_HO_042 | Referral code entry not triggering coin reward | Complete signup using valid referral code |  | Both referrer and referee receive coins | No coins credited to either party | Fail
CSM_HO_043 | Referral code is considered invalid even if it's shared from app | Copy-paste code from app to new device during sign-up |  | Code accepted and reward processed | Shows "Invalid referral code" | Fail
CSM_HO_044 | Referral tracking not working for shared links | Share link via WhatsApp and install app from it |  | App registers referrer from the link | No link between referrer and new user | Fail
CSM_HO_045 | Coins not updating in wallet after successful referral | Complete full referral flow |  | Wallet updates with referral coins | Wallet stays at zero | Fail
CSM_HO_046 | Verify carousel displays correctly | Open app home screen |  | Carousel loads and rotates banners | Carousel displays and slides as expected | Pass
CSM_HO_047 | Offers button shows available offers | Tap on "Offers" card |  | List of current offers shown | Offers list displayed properly | Pass
CSM_HO_048 | Events show Ongoing, Upcoming, and Past tabs | Tap on "Events" |  | Tabs display categorized events | Tabs load all event categories correctly | Pass
CSM_HO_049 | Events content loads correctly | Tap "Events" > Upcoming |  | List of upcoming events shown | Upcoming events shown | Pass
CSM_HO_050 | Location redirects to Google Maps | Tap "Location" card on home screen |  | Google Maps opens with mall location | No redirection or no response | Fail
CSM_HO_051 | My Vouchers button shows user vouchers | Tap "My Vouchers" |  | List of valid/expired vouchers shown | Vouchers listed as expected | Pass
CSM_HO_052 | Services button shows service list | Tap "Services" |  | List of all mall services shown | Services like wheelchair, parking shown | Pass
CSM_HO_053 | Movies button redirects to booking platform | Tap "Movies" |  | User is redirected to book movie tickets | External movie booking site opened | Pass
CSM_HO_054 | Vouchers for You section displays correctly | Tap on “Explore Vouchers for You” |  | Two sections visible: benefits and all vouchers | Both sections are shown | Pass
CSM_HO_055 | Benefit section shows correct tier (Silver/Gold/Platinum) | Open “Vouchers for You” | User in Silver tier | Silver benefit displayed with eligible vouchers | Silver tier and claimable vouchers shown | Pass
CSM_HO_056 | Eligible benefit vouchers are claimable | Tap “Claim” on a Silver benefit voucher | Valid user & claimable voucher | Voucher gets added to wallet | Voucher successfully claimed | Pass
CSM_HO_057 | All Vouchers section displays full voucher list | Scroll down to second section |  | Complete list of vouchers shown | Full voucher list loaded | Pass
CSM_HO_058 | Voucher filtering works by category | Use category dropdown to filter | Select “Food” | Only food vouchers shown | Correct filtered results | Pass
CSM_HO_059 | Voucher search returns relevant results | Use search box to type “Burger” | "Burger" | Related voucher(s) displayed | Correct results shown | Pass
CSM_HO_060 | Facebook icon redirects to mall’s FB page | Tap Facebook icon in Home |  | Facebook app/site opens with page | Redirect successful | Pass
CSM_HO_061 | Instagram icon redirects properly | Tap Instagram icon |  | Instagram app/site opens with profile | Redirect successful | Pass
CSM_HO_062 | Twitter icon works correctly | Tap Twitter icon |  | Opens mall’s Twitter profile | Redirect successful | Pass
CSM_HO_063 | LinkedIn icon redirects to LinkedIn page | Tap LinkedIn icon |  | Opens LinkedIn company profile | Redirect successful | Pass
Stores
CSM_ST_064 | All Stores section is visible | Open Store module |  | All Stores list is displayed | All stores displayed | Pass
CSM_ST_065 | Search bar is visible and functional | Type store name in search bar | footware | Matching store(s) shown | Lifestyle store displayed | Pass
CSM_ST_066 | Store filter options are displayed | Tap on Filter icon | N/A | Category filter options shown | Filter categories like Beauty, Food shown | Pass
CSM_ST_067 | Filtering stores by category works | Select “Beauty” filter | Beauty | Only beauty-related stores shown | Filtered list shown correctly | Pass
CSM_ST_068 | Filter + search combo works correctly | Filter: “unisex fashion” + Search: “Levis” | Filter: “unisex fashion” + Search: “Levis” | Matching store(s) shown in filtered context | Correct result shown | Pass
CSM_ST_069 | Favorite section displays liked stores | Navigate to “Favorites” tab | Liked stores exist | Only favorite stores shown | Favorite list appears correctly | Pass
CSM_ST_070 | No stores in favorite shows empty state | View Favorites tab without any liked stores | No liked stores | Message like “No favorites yet” displayed | Proper empty message shown | Pass
CSM_ST_071 | Liking a store adds it to favorites | Tap heart icon on store | Any store | Store gets added to Favorites | Store moved to Favorites tab | Pass
CSM_ST_072 | Unliking a store removes it from favorites | Unselect heart icon on a liked store | Liked store | Store removed from Favorites | Store disappears from Favorites list | Pass
CSM_ST_073 | Verify multiple category filters can be selected | Try selecting “Beauty” and “Food” together | Apply multiple filters | User can select more than one filter | Only one filter can be applied at a time | Fail
Loyalty
CSM_LY_074 | Verify Rewards section displays tier and coins | Go to Loyalty > Rewards | Logged-in user | User tier (Silver/Gold/etc.) and total coins shown | Rewards info displayed correctly | Pass
CSM_LY_075 | Explore section lists available coin vouchers | Tap “Explore” under Rewards |  | List of redeemable vouchers with required coins shown | Voucher list visible with coin values | Pass
CSM_LY_076 | User cannot redeem voucher without enough coins | Try to redeem a voucher with insufficient coins | User with low balance | Error message shown and redemption prevented | Redemption blocked as expected | Pass
CSM_LY_077 | User can redeem voucher if coins are sufficient | Tap redeem on a voucher with enough coins | free Voucher | Voucher is claimed and coins deducted | Voucher added to My Vouchers | Pass
CSM_LY_078 | My Vouchers displays claimed vouchers | Tap “My Vouchers” under Rewards | User with claimed vouchers | List of redeemed vouchers shown | Claimed vouchers appear | Pass
CSM_LY_079 | Transactions show coin usage per voucher | Go to Transactions tab |  | Shows voucher name and coin deduction details | All transactions listed with coin info | Pass
CSM_LY_080 | My Bills displays submitted and reviewed bills | Open “My Bills” tab |  | List of submitted, approved, and rejected bills shown | All bill statuses visible | Pass
CSM_LY_081 | Submitted bill shows status “Under Review” | Submit a new bill | Fresh bill | Status set as “Under Review” | Status shown as expected | Pass
CSM_LY_082 | Approved bill is listed under claimed bills | View My Bills after approval | Approved bill | Shown under Claimed Bills section | Appears correctly | Pass
CSM_LY_083 | Rejected bill is visible with reason | View rejected bills list | Rejected bill | Shows rejection with reason if any | Rejected bill visible | Pass

## Bug_Report
Centre Square Mall
VERSION NO: BROWSER:Chrome OS:Android |  |  |  | DATE:15/05/25
VERIFIED BY: |  |  |  | TESTED BY:Adarsh A S
Authentication
BUG_ID | TEST_ID | BUG_DESCRIPTION | STEPS TO REPRODUCE | SCREENSHOTS | SEVERITY | PRIORITY | Status
DEF_AU_001 | CSM_AU_003 | Register with improper city | Launch app → Register → Fill all valid fields → Submit |  | Medium | p1 | New
DEF_AU_002 | CSM_AU_004 | Register with existing email | Use an already registered email |  | High | p2 | New
DEF_AU_004 | CSM_AU_009 | Re-register with deleted account number | Delete account → Try registering again |  | High | p2 | New
MY Account
DEF_MA_005 | CSM_MA_017 | update with improper city | Change Name field |  | Medium | p1 | New
DEF_MA_006 | CSM_MA_021 | View my referrels | Launch app → Profile → my referels |  | Medium | p1 | New
DEF_MA_007 | CSM_MA_035 | Submit feedback with no character limit validation | Launch app → Profile → Feedback |  | Low | p1 | New
DEF_MA_008 | CSM_MA_036 | Submit very long feedback with 1000+ characters | Launch app → Profile → Feedback |  | Low | p1 | New
Home
DEF_HO_009 | CSM_HO_040 | Referral link is not working | Launch app → Home → refer now |  | Medium | p1 | New
DEF_HO_010 | CSM_HO_041 | No field to enter referral code during signup | Sign up with a fresh number |  | Medium | p1 | New
DEF_HO_011 | CSM_HO_042 | Referral code entry not triggering coin reward | Complete signup using valid referral code |  | Medium | p1 | New
DEF_HO_012 | CSM_HO_043 | Referral code is considered invalid even if it's shared from app | Copy-paste code from app to new device during sign-up |  | Medium | p1 | New
DEF_HO_013 | CSM_HO_044 | Referral tracking not working for shared links | Share link via WhatsApp and install app from it |  | Medium | p1 | New
DEF_HO_014 | CSM_HO_045 | Coins not updating in wallet after successful referral | Complete full referral flow |  | Medium | p1 | New
DEF_HO_015 | CSM_HO_050 | Location redirects to Google Maps | Tap "Location" card on home screen |  | Medium | p1 | New
Stores
DEF_ST_016 | CSM_ST_073 | Verify multiple category filters can be selected | Try selecting “Beauty” and “Food” together |  | Medium | p1 | New

## Def_Dis
DEFECT DISTRIBUTION GRAPH
MODULE NAME | DEFECT DISTRIBUTION
Authentication | 3
MY Account | 4
Home | 7
Stores | 1
Loyalty | 0
UI/UX | 0

## Test_Report
SL NO | MODULE NAME | TESTCASE PASSED | TESTCASE FAILED | TOTAL TESTCASE
1 | Authentication | 6 | 3 | 9
2 | MY Account | 26 | 4 | 30
3 | Home | 17 | 7 | 24
4 | Stores | 9 | 1 | 10
5 | Loyalty | 10 | 0 | 10